## Sheet1
Area | Working Package | Time Span | Description
Core | Movement | 29.4.2022 – 6.5.2022 | Create movement with input over joystick.
Core | Character Rotation | 29.4.2022 – 6.5.2022 | Create character rotation with input over joystick.
Core | Color Ground Shader | 29.4.2022 – 6.5.2022 | Create a shader that covers the ground in a specific area in a specific color. This color can then be overwritten with another color.
Core | Color Score Calculation | 29.4.2022 – 6.5.2022 | The color score should be calculated through the amount of area that is painted by the players.
Core | Color Trail | 29.4.2022 – 13.5.2022 | Create a color trail that folows the player.
Core | Map Creation | 29.4.2022 – 13.5.2022 | Create a map with obstacles and holes.
Shooting | Projectile Shooting | 6.5.2022 – 13.5.2022 | Create a projectile that flies across the arena.
Shooting | Projectile Explosion | 6.5.2022 – 13.5.2022 | The projectile explodes on impact and paints everything around the impact point.
Graphics | Different Materials Fitting the Theme | 6.5.2022 – 20.5.2022 | Create materials in the theme of Tron (glossy black contrasted with neon colors).
Shooting | Projectile Charging | 13.5.2022 – 20.5.2022 | The projectile can be charged and therefore gets bigger and/or faster.
Shooting | Projectile Stun | 13.5.2022 – 20.5.2022 | The projectile stuns a player if it is in the explosion radius or directly hit.
Graphics | Character Movement Animation | 13.5.2022 – 20.5.2022 | Create animations for running and dashing.
Extended Gameplay | Dash | 13.5.2022 – 20.5.2022 | A player should be able to dash in order to dodge projectiles and dashes should have a cooldown.
Graphics | Color Score Display | 20.5.2022 – 27.5.2022 | The color score should be displayed and updated regularly so that the players can see their amount of colored surface.
Extended Gameplay | Stun Holes | 20.5.2022 – 27.5.2022 | If a player gets pushed into a hole, they will be stunned.
Graphics | Shooting and Stun Animations | 20.5.2022 – 31.5.2022 | Create animations for being stunned, shooting and charging the projectile.
Core | Time based score system | 29.4.2022 – 6.5.2022 | After a specific time was reached, the player with the most covered area wins