## Sheet1
Area | Working Package | Time Span | Description | Status |  | Status
Core | Movement | 29.4.2022 – 6.5.2022 | Create movement with input over joystick. | Done |  | 3
Core | Character Rotation | 29.4.2022 – 6.5.2022 | Create character rotation with input over joystick. | Done |  | 3
Core | Color Ground Shader | 29.4.2022 – 6.5.2022 | Create a shader that covers the ground in a specific area in a specific color. This color can then be overwritten with another color. | Done |  | 13
Core | Color Score Calculation | 29.4.2022 – 6.5.2022 | The color score should be calculated through the amount of area that is painted by the players. | Done | Not done if moved to shader | 8
Core | Color Trail | 29.4.2022 – 13.5.2022 | Create a color trail that folows the player. | Done |  | 5
Core | Map Creation | 29.4.2022 – 13.5.2022 | Create a map with obstacles and holes. | Done | Manual Map Generation | 2
Shooting | Projectile Shooting | 6.5.2022 – 13.5.2022 | Create a projectile that flies across the arena. | Done |  | 3
Shooting | Projectile Explosion | 6.5.2022 – 13.5.2022 | The projectile explodes on impact and paints everything around the impact point. | Done |  | 5
Graphics | Different Materials Fitting the Theme | 6.5.2022 – 20.5.2022 | Create materials in the theme of Tron (glossy black contrasted with neon colors). | Done |  | 2
Shooting | Projectile Charging | 13.5.2022 – 20.5.2022 | The projectile can be charged and therefore gets bigger and/or faster. | Done |  | 2
Shooting | Projectile Stun | 13.5.2022 – 20.5.2022 | The projectile stuns a player if it is in the explosion radius or directly hit. | Done | Changed to knockback | 1
Graphics | Character Movement Animation | 13.5.2022 – 20.5.2022 | Create animations for running and dashing. | Done |  | 5
Extended Gameplay | Dash | 13.5.2022 – 20.5.2022 | A player should be able to dash in order to dodge projectiles and dashes should have a cooldown. | Done |  | 5
Graphics | Color Score Display | 20.5.2022 – 27.5.2022 | The color score should be displayed and updated regularly so that the players can see their amount of colored surface. | Done |  | 3
Extended Gameplay | Stun Holes | 20.5.2022 – 27.5.2022 | If a player gets pushed into a hole, they will be stunned. | Done |  | 1
Graphics | Shooting and Stun Animations | 20.5.2022 – 31.5.2022 | Create animations for being stunned, shooting and charging the projectile. | Done |  | 5
Core | Time based score system | 29.4.2022 – 6.5.2022 | After a specific time was reached, the player with the most covered area wins | Done |  | 1
[6 empty] | 67 | Total SP | 1 SP = 1 Hour
[6 empty] | 67 | Done